CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, Jan 2025 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Cost & Time Estimations	4

1.2 Project Objectives	6

1.3 Project Risks	7

2. Management Approach	8

2.1 Project Processes	8

2.2 Quality Management	10

2.3 Project Training Plan	11

3. Responsibility Assignments	11

4. Project Communications	13

5. Configuration Management	15

5.1 Document Management	15

5.2 Source Code Management	15

5.3 Tools & Infrastructures	16

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 21/01/2026 | A | LinhVTK | Add Overview, Management Approach, Responsibility Assignments, Project Communications, Configuration Management |
| 22/01/2026 | M | LinhVTK | Modify Responsibility Assignments, Project Communications, Configuration Management |
| 03/02/2026 | M | LinhVTK | Modify Management Approach |
| 24/03/2026 | M | LinhVTK | Modify Project Training Plan |
| 16/04/2026 | M | LinhVTK | Modify Management Approach |
| 26/04/2026 | M | LinhVTK | Modify Project Objectives, Quality Management |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Cost & Time Estimations

| # | Work Package | Est. Effort (pds) | Deadline |
| --- | --- | --- | --- |
| 1 | Stage 1: Project Initiating (week 1) | 15 |  |
| 1.1 | Report 1 (Project Introduction) | 15 | Week1 |
| 2. | Stage 2: Project Planning & Initial Requirements (weeks 2-3) | 40 |  |
| 2.1 | Report 3: SRS v0.9 (Overall Requirement) | 15 | Week2 |
| 2.2 | Vertical Prototypes (Code Demo) | 15 | Week3 |
| 2.3 | Report 2: Project Management Plan v1.0 | 10 | Week3 |
| 3 | Stage 3: Software Design (weeks 4-5) | 50 |  |
| 3.1 | Vertical Prototypes (POC, or Proof Of Concepts) | 15 | Week4 |
| 3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | 15 | Week4 |
| 3.3 | Report 5: Test Planning (ref Report5_Test Documentation) | 10 | Week5 |
| 3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 10 | Week5 |
| 4 | Stage 4: Implementation (weeks 6-11) (Ref: Project Tracking, WBS sheet) | 185 |  |
| 4.1 | Implementation Iteration 1 (weeks 6-7) | 60 |  |
| 4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.1 | 10 | Week6 |
| 4.1.2 | Code Package & Unit Testing Report | 30 | Week6 |
| 4. 1.3 | Report 5: Integration Test Cases | 5 | Week6 |
| 4. 1.4 | Report 5: Integration Test Report | 5 | Week7 |
| 4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 5 | Week7 |
| 4.1.6 | Software Package Version 1 | 5 | Week7 |
| 4.2 | Implementation Iteration 2 (weeks 8-9) | 6 |  |
| 4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 5 | Week8 |
| 4.2.2 | Code Package & Unit Testing Report | 10 | Week8 |
| 4. 2.3 | Report 5: Integration Test Cases | 35 | Week8 |
| 4. 2.4 | Report 5: Integration Test Report | 5 | Week9 |
| 4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 5 | Week9 |
| 4.2.6 | Software Package Version 2 | 5 | Week9 |
| 4.3 | Implementation Iteration 3 (weeks 10-11) | 60 |  |
| 4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 10 | Week10 |
| 4.3.2 | Code Package & Unit Testing Report | 30 | Week10 |
| 4.3.3 | Report 5: Integration Test Cases | 5 | Week10 |
| 4.3.4 | Report 5: Integration Test Report | 5 | Week11 |
| 4.3.5 | Report 5: System Test Cases | 5 | Week11 |
| 4.3.6 | Software Package Version 3 | 5 | Week11 |
| 5 | Stage 5: Verification & Validation (weeks 12-13) | 45 |  |
| 5.1 | Report 5: System Test Report | 15 | Week12 |
| 5.2 | Report 6: User Guides (Installation Guides, User Manuals) | 10 | Week12 |
| 5.3 | Acceptance Test and Support | 10 | Week13 |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | 10 | Week13 |
| 6 | Stage 6: Closing (week 14) | 15 |  |
| 6.1 | Report 7: Final Project Report | 10 | Week14 |
| 6.2 | Presentation File | 5 | Week14 |

Table 1: Scope and Estimation

### 1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | 350 | 330 | Compare with actual in Project Tracking (Scope sheet). |
| 2 | Unit Test Defects | No of defects | 40 | 0 | From unit test reports per iteration. |
| 3 | Integration Test Defects | No of defects | 30 | 0 | From integration test reports. |
| 4 | System Test Defects | No of defects | 30 | 0 | From system test report. |
| 5 | Acceptance Test Defects | No of defects | 10 | 0 | From UAT/acceptance test results. |
| 6 | Timeliness | % | 90% | 90% | On-time deliverables / Total deliverables. |
| 7 | Requirement Completeness | % | 90% | 90% | Failed if ≤ 75%. |
| 8 | User Satisfaction | % | 90% | 90% | From demo feedback / survey with supervisor/lecturer. |

Table 2: Project Objectives

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Potential for internal conflicts or ineffective communication among team members | High | Medium | Mitigate by organizing frequent progress meetings and utilizing primary communication platforms such as Google Meet, Messenger, and Zalo. |
| 2 | Integration risk associated with third-party services such as AI libraries, cloud storage,and authentication protocols. | High | Low - Medium | Establish a clear system architecture and standardize APIs to ensure seamless connectivity. Additionally, implement sandbox environments early and design fallback mechanisms to maintain functionality during external service failures. |
| 3 | Performance issues when the number of users and courses increases | Medium - High | Medium | Design scalable system architecture, perform load testing, optimize database queries and caching mechanisms. |

Table 3:Project Risks

## 2. Management Approach

### 2.1 Project Processes

The Nova Learning Management System (Nova LMS) is developed using the Iterative and Incremental Development Model. This model is selected to ensure flexibility, continuous improvement, and early delivery of functional system components throughout the development process.

Figure 1: Iterative and Incremental model

Nova LMS is composed of multiple functional modules, including User & Authentication, Course Management, Class Management, Learning Enrollment, Course Content, Question Bank, Quiz–Assessment, System Dashboard, and System Configurations. Due to the modular structure, the system is developed in multiple iterations, where each iteration focuses on a specific set of features. Core functionalities are prioritized and implemented in early iterations, while additional features are developed in later stages.

The project is divided into iterations of approximately two weeks. In each iteration, the team performs a complete development cycle, including planning, requirement analysis, system design, implementation, testing, and review. At the end of each iteration, the developed features are evaluated before proceeding to the next iteration.

This development model is suitable for Nova LMS because system requirements may evolve during development. Feedback from testing and stakeholders may lead to adjustments in features and functionalities. The iterative approach allows the team to manage these changes effectively, reduce risks, and continuously improve the system.

Requirement and Scope Management

The initial development focuses on core LMS functionalities such as user management, course management, and learning features. Each iteration has a clearly defined scope to ensure controlled development and avoid scope creep. New or updated requirements are documented and planned for future iterations.

Change Management

All requirement changes are reviewed between iterations. Each change is analyzed based on its impact on system functionality, development effort, and timeline. Approved changes are incorporated into subsequent iterations.

Time Management

Each iteration is planned with specific objectives and deliverables. Progress is reviewed at the end of each iteration to ensure the project stays on schedule.

Development, Monitoring, and Control

Each iteration follows a structured workflow: Planning → Analysis → Design → Implementation → Testing → Review.

Source code is managed using Git to support version control and collaboration. Issues and risks are identified early and addressed in subsequent iterations to ensure continuous improvement and system stability.

### 2.2 Quality Management

Quality management for the Nova LMS is applied throughout the development process to ensure that the system meets functional requirements, maintains stability, and supports maintainability.

Quality Activities:

Requirement and Design Review

Requirement documents and system designs are reviewed within the team before implementation in each iteration. This helps ensure that requirements are clear, feasible, and aligned with system objectives.

Code Review

Source code is reviewed by team members after completing key functionalities. Feedback from code reviews is used to improve code quality, consistency, and maintainability.

Testing Strategy

- Unit Testing (UT): Developers perform unit testing on individual functions or components to ensure correctness before integration.

- Integration Testing: Newly developed features are tested with existing modules to ensure proper interaction between components.

- Regression Testing: Previously implemented features are re-tested after each iteration to ensure that new changes do not break existing functionalities.

- System Testing (ST): The system is tested as a whole to verify that all integrated features work correctly according to requirements.

- Acceptance Testing (AT): Basic acceptance testing is conducted to validate that the system meets expected user requirements and scenarios.

Defect Management

Defects identified during testing are recorded, tracked, and prioritized for fixing. Critical issues are resolved within the same iteration, while minor issues are scheduled for future iterations.

Quality Monitoring and Improvement

Testing results and feedback are reviewed at the end of each iteration. Lessons learned are documented and applied to improve development practices and reduce defects in subsequent iterations.

### 2.3 Project Training Plan

| Training Area | Participants | When, Duration |
| --- | --- | --- |
| Java Spring Boot & Thymleaf | DatMN, ThanhMC, TuNC, AnhDHD | From 20/01/2026 to 26/01/2026 (7 days) |
| Git, GitHub | DatMN, ThanhMC, TuNC, AnhDHD, LinhVTK | From 24/01/2026 to 26/01/2026 (3 days) |
| Database Design | DatMN, ThanhMC, TuNC, AnhDHD | From 27/01/2026 to 29/01/2026 (3 days) |

Table 4:Project Training Plan

## 3. Responsibility Assignments

Figure 2: Project Organization Chart

Link: Project Organization Chart

RASCI Chart: R~Responsible, A~Accountable, S~Support, C~Consulted, I~Informed

| Work Package | DatMN | LinhVTK | AnhDHD | ThanhMC | TuNC |
| --- | --- | --- | --- | --- | --- |
| Stage 1 – Project Initiating |  |  |  |  |  |
| Project Introduction (Report 1) | A | R | S | S | S |
| Stage 2 – Planning & Initial Requirements |  |  |  |  |  |
| Project Management Plan v1.0 (Report 2) | A | S | I | I | I |
| SRS v0.9 – Overall Requirements (Report 3) | C | R | S | S | S |
| Vertical Prototype (Code Demo) | C | S | R | R | R |
| Stage 3 – Software Design |  |  |  |  |  |
| POC / Vertical Prototype | C | S | R | R | R |
| SDS v1.0 – High-level Design (Report 4) | C | S | R | R | R |
| Test Planning (Report 5) | I | A | S | S | S |
| SRS v1.0 – Iteration 1 | C | R | S | S | S |
| Stage 4 – Implementation (Iteration 1) |  |  |  |  |  |
| SDS v1.1 | C | S | R | R | R |
| Code Package & Unit Testing | I | C | R | R | R |
| Integration Test Cases | I | R | S | S | S |
| Integration Test Report | I | A | S | S | S |
| SRS v1.1 – Iteration 2 | C | R | S | S | S |
| Software Package Version 1 | A | C | R | R | R |
| Stage 4 – Implementation (Iteration 2) |  |  |  |  |  |
| SDS v1.2 | C | S | R | R | R |
| Code Package & Unit Testing | I | C | R | R | R |
| Integration Test Cases | I | R | S | S | S |
| Integration Test Report | I | A | S | S | S |
| SRS v1.2 – Iteration 3 | C | R | S | S | S |
| Software Package Version 2 | A | C | R | R | R |
| Stage 4 – Implementation (Iteration 3) |  |  |  |  |  |
| SDS v1.3 | C | S | R | R | R |
| Code Package & Unit Testing | I | C | R | R | R |
| System Test Cases | I | R | S | S | S |
| System Test Report | I | A | S | S | S |
| Software Package Version 3 | A | C | R | R | R |
| Stage 5 – Verification & Validation |  |  |  |  |  |
| User Guides (Report 6) | C | R | S | S | S |
| Acceptance Test | A | R | S | S | S |
| Final Software Package | A | C | R | R | R |
| Stage 6 – Closing |  |  |  |  |  |
| Final Project Report (Report 7) | A | R | S | S | S |
| Presentation File | A | R | S | S | S |

Table 5:Responsibility Assignments

## 4. Project Communications

| Communication Item | Who / Target | Purpose | When / Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Iteration Planning Meeting | Entire Team, Instructor | Define objectives, scope, and deliverables for the current iteration | Beginning of each iteration | Meeting (offline or Google Meet) |
| Daily Progress Sync | Entire Team | Synchronize progress, identify issues, and plan daily work | Daily (short meeting) | Online meeting (Google Meet), notes |
| Iteration Review & Demo | Team, Instructor, Stakeholders | Demonstrate completed functions and collect feedback for next iteration | End of each iteration | Online demo (Google Meet), recorded demo video |
| Iteration Retrospective | Development Team | Review working process and identify improvements for the next iteration | End of each iteration | Internal meeting, retrospective notes |
| Weekly Progress Report | Team, Instructor | Summarize completed work, risks, issues, and next iteration plan | Weekly | Report via Google Docs, brief review meeting |
| Requirement Discussion & Clarification | Project Manager, BA, Developers | Clarify and refine requirements for current or next iteration | As needed | Meeting via Google Meet, Zalo chat |
| Ad-hoc Technical Coordination | Developers | Resolve technical and integration issues during iteration | As needed | Zalo chat, quick Google Meet call |
| Document Sharing & Version Control | Entire Team | Maintain updated documents and source code for each iteration | Continuous | Google Drive (documents), GitHub (source code) |
| Urgent Issue Escalation | Entire Team, Project Manager | Report critical defects, blockers, or schedule risks | Immediate | Zalo call, Zalo group chat |
| Instructor Consultation | Project Manager, Key Members | Receive guidance and feedback for ongoing or upcoming iterations | Bi-weekly or as needed | Meeting via Google Meet |

Table 6: Project Communications

## 5. Configuration Management

### 5.1 Document Management

Google Drive’s native version control mechanisms are applied for managing non-code documentation:

- Major Version Updates: For significant document changes or milestone releases, the Project Manager creates a new copy of the document and renames it with an incremented version number (e.g., v1.0, v2.0). This provides a clear snapshot of major document revisions and preserves historical versions.

- Integrated Version History: For minor edits and collaborative updates, the team uses Google Drive’s built-in Version History feature to track changes, identify authors, and restore previous versions when necessary. This approach eliminates redundant file copies while maintaining full traceability.

### 5.2 Source Code Management

Source code for Nova LMS is managed using GitHub as the centralized version control repository. All developers follow a standardized branching and pull request workflow to ensure code quality and traceability.

Repository: https://github.com/thanhmjkeeeee/ISP490_G1_NovaLMS.git

Branching Strategy:

- Main branch: stable, production-ready code

- Develop branch: integration of completed features

- Feature branches: used for implementing individual features or bug fixes

Code Review and Merge Policy:

All code changes must be submitted through pull requests and reviewed by at least one team member before merging into the main branches. This ensures consistency, security, and maintainability of the codebase.

### 5.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java Spring Boot, Thymeleaf (Front-end), RESTful APIs |
| Database | MySQL |
| IDEs / Editors | IntelliJ IDEA, Visual Studio Code |
| Diagramming | DrawIO |
| Documentation | MS Office, Google Docs / Sheets |
| Version Control | GitHub (Source Code), Google Drive (Documents) |
| Deployment Server | Render, Railway. |
| Project Management | Google Sheet |
| Testing Tools | JUnit, Postman, JMeter |

Table 7: Tools & Infrastructures