## Scope
# | Work Package | Est. Effort (pds) | In Charge | Deadline | Status | Actual Effort (pds) | Notes
1 | Stage 1: Project Initiating (week 1) | 15 |  |  | Completed | 15
1.1 | Report 1 (Project Introduction) | 15 | LinhVTK | Week1 | Completed | 15
2 | Stage 2: Project Planning & Initial Requirements (weeks 2-3) | 40 |  |  |  | 40
2.1 | Report 3: SRS v0.9 (Overall Requirement) | 15 | All Members | Week2 | Completed | 15
2.2 | Vertical Prototypes (Code Demo) | 15 | ThanhMC | Week3 | Completed | 15
2.3 | Report 2: Project Management Plan v1.0 | 10 | LinhVTK | Week3 | Completed | 10
3 | Stage 3: Software Design (weeks 4-5) | 50 |  |  |  | 50
3.1 | Vertical Prototypes (POC, or Proof Of Concepts) | 15 | AnhDHD | Week4 | Completed | 15
3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | 15 | DATMN | Week4 | Completed | 15
3.3 | Report 5: Test Planning (ref Report5_Test Documentation) | 10 | LinhVTK | Week5 | Completed | 10
3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 10 | All Members | Week5 | Completed | 10
4 | Stage 4: Implementation (weeks 6-11) | 185 |  |  |  | 175
4.1 | Implementation Iteration 1 (weeks 6-7) | 60 |  |  |  | 55
4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.1 | 10 | DATMN | Week6 | Completed | 10
4.1.2 | Code Package & Unit Testing Report | 30 | TUNC | Week6 | Completed | 25
4. 1.3 | Report 5: Integration Test Cases | 5 | LinhVTK | Week6 | Completed | 5
4. 1.4 | Report 5: Integration Test Report | 5 | LinhVTK | Week7 | Completed | 5
4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 5 | LinhVTK | Week7 | Completed | 5
4.1.6 | Software Package Version 1 | 5 | ThanhMC | Week7 | Completed | 5
4.2 | Implementation Iteration 2 (weeks 8-9) | 65 |  |  |  | 65
4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 5 | DATMN | Week8 | Completed | 10
4.2.2 | Code Package & Unit Testing Report | 10 | AnhDHD | Week8 | In Progress | 10
4. 2.3 | Report 5: Integration Test Cases | 35 | LinhVTK | Week8 | Completed | 30
4. 2.4 | Report 5: Integration Test Report | 5 | LinhVTK | Week9 | Completed | 5
4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 5 | LinhVTK | Week9 | Completed | 5
4.2.6 | Software Package Version 2 | 5 | ThanhMC | Week9 | Completed | 5
4.3 | Implementation Iteration 3 (weeks 10-11) | 60 |  |  |  | 55
4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 10 | DATMN | Week10 | Completed | 10
4.3.2 | Code Package & Unit Testing Report | 30 | TuNC | Week10 | Completed | 25
4.3.3 | Report 5: Integration Test Cases | 5 | LinhVTK | Week10 | Completed | 5
4.3.4 | Report 5: Integration Test Report | 5 | LinhVTK | Week11 | Completed | 5
4.3.5 | Report 5: System Test Cases | 5 | LinhVTK | Week11 | Completed | 5
4.3.6 | Software Package Version 3 | 5 | ThanhMC | Week11 | Completed | 5
5 | Stage 5: Verification & Validation (weeks 12-13) | 45 |  |  |  | 35
5.1 | Report 5: System Test Report | 15 | LinhVTK | Week12 | Completed | 10
5.2 | Report 6: User Guides (Installation Guides, User Manuals) | 10 | LinhVTK | Week12 | Completed | 10
5.3 | Acceptance Test and Support | 10 | LinhVTK | Week13 | Completed | 5
5.4 | Final Software Package (Documents, Source Codes, etc.) | 10 | ThanhMC | Week13 | Completed | 10
6 | Stage 6: Closing (week 14) | 15 |  |  |  | 15
6.1 | Report 7: Final Project Report | 10 | LinhVTK | Week14 | Completed | 10
6.2 | Presentation File | 5 | All Members | Week14 | Completed | 5

## WBS
Function/Screen | Type | Feature | Actor | Implement | Function/Screen Description | Sum( | Est. Effort | Planned | Status | Notes
Home Page | Screen | User Authentication | Guest | Đức Anh | The homepage introduces the platform and displays featured courses. | Simple | 6 | Iteration 1 | Completed
Class Schedule | Screen | Class Management | Guest | Đức Anh | Displays the tentative class start dates, allowing students to easily see the start times of upcoming courses. | Simple | 3 | Iteration 1 | Completed
Public Courses List | Screen | Course Management | Guest | Đức Anh | A complete list of all courses currently being published. | Simple | 3 | Iteration 1 | Completed
Public Courses Detail | Screen | Course Management | Guest | Đức Anh | Course details include: description, curriculum (modules), instructors, and tuition fees. | Medium | 6 | Iteration 1 | Completed
User Register | Screen | User Authentication | Guest | Đức Anh | This is a registration form for new students, requiring email address, full name, and password. | Medium | 8 | Iteration 1 | Completed
User Login | Screen | User Authentication | Guest | Thanh | The system login page supports login using internal accounts and integrates login via Google. | Simple | 6 | Iteration 1 | Completed
Reset Password | Screen | User Authentication | Admin, Student, Manager, Teacher, Expert | Thanh | The password recovery process involves sending a verification code to the user's email address. | Medium | 8 | Iteration 1 | Completed
User Profile | Screen | User Authentication | Admin, Student, Manager, Teacher, Expert | Thanh | Manage students' personal information such as avatars, gender, and contact information. | Medium | 6 | Iteration 1 | Completed
Password Change | Screen | User Authentication | Admin, Student, Manager, Teacher, Expert | Thanh | The password change process by the user | Simple | 3 | Iteration 1 | Completed
Student Dashboard | Screen | System Dashboard | Student | Thanh | The main screen, after a student logs in, displays an overview of their learning progress and the courses they are currently enrolled in. | Medium | 8 | Iteration 3 | Completed
Course/Class Payment | Screen | Learning Enrollment | Student | Đức Anh | The payment confirmation interface is integrated with the PayOS payment gateway when students register for courses or classes. | Complex | 20 | Iteration 2 | Completed
Payment Result | Screen | Learning Enrollment | Student | Đức Anh | Display the status after the transaction is complete, confirming that the student has been successfully enrolled. | Simple | 3 | Iteration 2 | Completed
Course Payment History | Screen | Learning Enrollment | Student, Admin, Manager | Đức Anh | Transaction history and tuition payment status of students (Approved/Pending). | Simple | 3 | Iteration 2 | Completed
Enrolled Courses | Screen | Learning Enrollment | Student | Đức Anh | This is a list of courses that the student has successfully registered for and is currently enrolled in. | Simple | 3 | Iteration 2 | Completed
Enrolled Course Content | Screen | Course Content | Student | Thanh | The detailed course roadmap structure of the purchased course allows access to each module and lesson. | Medium | 8 | Iteration 2 | Completed
Lesson Viewer | Screen | Course Content | Student | Thanh | The main learning interface includes: video lectures, text content (Reading), downloadable attachments, and lesson completion marking. | Medium | 10 | Iteration 2 | Completed
Assessment Attempt | Screen | Quiz-Assessment | Student | Thanh | This screen displays the online test. It supports all four skills, includes a countdown timer, and automatically saves the test results. | Complex | 28 | Iteration 3 | Completed
Assessment Results | Screen | Quiz-Assessment | Student | Thanh | Display the results of the assignment after submission, including score, correct/incorrect answers, and feedback from the AI ​​and the teacher. | Medium | 8 | Iteration 3 | Completed
Enrolled Classes | Screen | Learning Enrollment | Student | Tứ | A list of the practical courses that students are currently enrolled in. | Simple | 3 | Iteration 1 | Completed
Enrolled Class Details | Screen | Learning Enrollment | Student | Tứ | Detailed information about the course: Instructor, class size, regular class schedule, and online classroom link (Zoom/Meet). | Medium | 8 | Iteration 1 | Completed
Assessment Overview | Screen | Quiz-Assessment | Student | Thanh | This summarizes your test completion history and progress throughout the course. | Medium | 5 | Iteration 2 | Completed
Manager Dashboard | Screen | System Dashboard | Manager | Tứ | Statistics on new registrations and classroom performance metrics. | Medium | 8 | Iteration 3 | Completed
Class List | Screen | Class Management | Manager, Admin | Tứ | A complete list of all classes in the system, managed by status (Open/Pending/Closed). | Simple | 4 | Iteration 1 | Completed
New Class | Screen | Class Management | Manager, Admin | Tứ | This form allows you to create a new class, assign instructors, select the original course, and set up a schedule. | Medium | 10 | Iteration 2 | Completed
Class Details | Screen | Class Management | Manager, Admin | Tứ | Manage class details, edit operational information, and track the list of sessions. | Medium | 8 | Iteration 1 | Completed
Schedule Review | Screen | Class Management | Manager, Admin | Tứ | Approve or reject schedule change requests submitted by teachers. | Simple | 6 | Iteration 1 | Completed
Teacher Dashboard | Screen | System Dashboard | Teacher | Tứ | Displays the teaching schedule for the day and notifies you about assignments recently submitted by students that need grading. | Medium | 8 | Iteration 2 | Completed
Class Workspace | Screen | Class Management | Teacher | Thanh | This is the teacher's main workspace for each class, where they manage lesson materials and interact with students. | Complex | 16 | Iteration 2 | Completed
Assessment Grading | Screen | Quiz-Assessment | Teacher | Thanh | List of student assignments (Speaking/Writing) awaiting teacher grading. | Complex | 18 | Iteration 3 | Completed
Question Submissions | Screen | Question Bank | Teacher | Tứ | Manages teachers' individual question banks, where teachers can contribute questions to the system. | Medium | 6 | Iteration 3 | Completed
Expert Dashboard | Screen | System Dashboard | Expert | Đạt | Statistics on question banks, the number of questions compiled, and the content review status. | Simple | 4 | Iteration 2 | Completed
Expert Courses | Screen | Course Management | Expert/Admin | Đạt | Manage the list of courses for which the Expert is responsible for content creation. | Simple | 3 | Iteration 2 | Completed
Chapter List | Screen | Course Content | Expert/Admin | Đạt | Design the module (chapter) structure for each course and manage the teaching order. | Medium | 3 | Iteration 2 | Completed
Chapter Detail | Screen | Course Content | Expert/Admin | Đạt | Design the module (chapter) structure for each course and manage the teaching order. | Medium | 6 | Iteration 2 | Completed
Lesson Details | Screen | Course Content | Expert/Admin | Đạt | Design the lesson structure for each course and manage the teaching order. | Simple | 3 | Iteration 2 | Completed
Question List | Screen | Question Bank | Expert/Admin | Đạt | The system's overall question bank supports filtering by skill level (L-R-W-S) and CEFR level. | Medium | 6 | Iteration 2 | Completed
New Question | Screen | Question Bank | Expert/Admin | Đạt | Manual question creation form with various question types (Multiple choice, Fill in blank, Matching...). | Complex | 16 | Iteration 2 | Completed
Question Generator | Screen | Question Bank | Expert/Admin | Đạt | These AI-powered tools automatically generate questions based on keywords, lesson content, or text snippets. | Complex | 22 | Iteration 3 | Completed
Question Detail | Screen | Question Bank | Expert/Admin | Đạt | Manual question creation form with various question types (Multiple choice, Fill in blank, Matching...). | Simple | 3 | Iteration 2 | Completed
Assessment List | Screen | Quiz-Assessment | Expert/Admin | Đạt | Manage a catalog of sample exams, entrance tests, and homework assignments. | Simple | 3 | Iteration 3 | Completed
New Assessment | Screen | Quiz-Assessment | Expert/Admin | Đạt | New exam configuration: Set the time limit, passing score, and choose the question retrieval method. | Medium | 8 | Iteration 2 | Completed
Assessment Details | Screen | Quiz-Assessment | Expert/Admin | Đạt | Edit the exam configuration and view the exam's publication status. | Simple | 4 | Iteration 3 | Completed
AI Prompt Configs | Screen | System Configs | Expert/Admin | Đức Anh | Set technical parameters (Prompts) to control how the AI ​​generates questions for each level. | Medium | 8 | Iteration 3 | Completed
Question Review | Screen | Question Bank | Expert/Admin | Đạt | The process involves reviewing questions contributed by teachers before they are officially added to the shared question bank. | Complex | 3 | Iteration 3 | Completed
Admin Dashboard | Screen | System Dashboard | Admin | Tứ | System overview: Total users, revenue, registration graphs, and key activity logs. | Simple | 4 | Iteration 2 | Completed
Account List | Screen | User Authentication | Admin | Tứ | Manage all users in the system (Admin, Expert, Teacher, Manager, Student). | Simple | 8 | Iteration 3 | Completed
New Account | Screen | User Authentication | Admin | Tứ | Create new internal (employee) accounts and assign corresponding roles. | Medium | 5 | Iteration 2 | Completed
Account Detail | Screen | User Authentication | Admin | Tứ | Edit details, reset password, or lock a user's account. | Simple | 4 | Iteration 2 | Completed
Course List | Screen | Course Management | Admin | Tứ | Manage the course catalog at the system administrator level. | Simple | 3 | Iteration 1 | Completed
New Course | Screen | Course Management | Admin | Tứ | Create a new original course, setting up basic information about pricing and the instructor. | Simple | 8 | Iteration 1 | Completed
Course Detail | Screen | Course Management | Admin | Tứ | Review the course structure and details from an administrator's perspective. | Simple | 3 | Iteration 2 | Completed
Admin Settings | Screen | System Dashboard | Admin | Đức Anh | Configure system parameters such as Email Server, Role categories, and other Global settings. | Simple | 4 | Iteration 3 | Completed
Planned | Functions | Total Effort
Iteration 1 | 16 | 89
Iteration 2 | 23 | 154
Iteration 3 | 13 | 128
Grand Total | 52 | 371

## Defects
Project Defects
Date | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2026-03-05 | Error message 'Mật khẩu phải có ít nhất 6 ký tự!' is displayed | IT | Software Package | User Register | Thanh |  | Fixed
2026-03-05 | Check invalid email format | IT | Software Package | User Login | Thanh |  | Fixed
2026-03-05 | Check invalid phone number format | IT | Software Package | User Profile | Thanh |  | Fixed
2026-03-05 | Check required field validation (empty name) | IT | Software Package | New Account | Tứ |  | Fixed
2026-03-05 | Check required field validation (empty email) | IT | Software Package | New Account | Tứ |  | Fixed
2026-03-05 | Check invalid email format | IT | Software Package | New Account | Tứ |  | Fixed
2026-03-05 | Check back navigation | IT | Software Package | Account Details | Tứ |  | Fixed
2026-03-05 | Check filter "Tất cả" | IT | Software Package | Public Course List | Đức Anh |  | Fixed
2026-03-05 | Check pagination | IT | Software Package | Course List | Thanh |  | Fixed
2026-03-05 | Check lesson number validation | IT | Software Package | New Course | Thanh |  | Fixed
2026-03-05 | Check filter by status | IT | Software Package | Expert Courses | Đạt |  | Fixed
2026-03-05 | Check enrolled course information display | IT | Software Package | Enrolled Courses | Thanh |  | Fixed
2026-03-05 | Check course learning navigation | IT | Software Package | Enrolled Courses | Thanh |  | Fixed
2026-03-12 | Check search schedule | IT | Software Package | Class Schedule | Thanh |  | Fixed
2026-03-12 | Check request data display detail | IT | Software Package | Schedule Review | Thanh |  | Fixed
2026-03-12 | Check tab navigation | IT | Software Package | Class Workspace | Đạt |  | Fixed
2026-03-13 | Check continue learning button | IT | Software Package | Course/Class Payment | Đức Anh |  | Fixed
2026-03-13 | Check invalid order value | IT | Software Package | Course/Class Payment | Đức Anh |  | Fixed
2026-03-13 | Check invalid order value | IT | Software Package | Chapter Details | Thanh |  | Fixed
2026-03-22 | Check audio playback | IT | Software Package | Assessment Attempt | Thanh |  | Fixed
2026-03-22 | Check pass/fail status | IT | Software Package | Assessment Results | Thanh |  | Fixed
2026-03-22 | Check chart display | IT | Software Package | Assessment Results | Thanh |  | Fixed
2026-03-22 | Check search assessment | IT | Software Package | Assessment Overview | Thanh |  | Fixed
2026-03-22 | Check search assessment | IT | Software Package | Assessment List | Thanh |  | Fixed
2026-03-22 | Check cancel action | IT | Software Package | Assessment Details | Thanh |  | Fixed
2026-03-22 | Check submit final grading | IT | Software Package | Assessment Grading | Thanh |  | Fixed
2026-03-23 | Check duplicate name validation | IT | Software Package | Admin Settings | Đức Anh |  | Fixed
2026-03-23 | Check add grammar topic | IT | Software Package | AI Prompt Configs | Đức Anh |  | Fixed
2026-03-26 | Check required field validation (empty skill) | IT | Software Package | New Question | Đạt |  | Fixed
2026-03-26 | Check required field validation (empty level) | IT | Software Package | New Question | Đạt |  | Fixed
2026-03-26 | Check select question type (single question) | IT | Software Package | New Question | Đạt |  | Fixed
2026-03-26 | Check select question type (passage) | IT | Software Package | New Question | Đạt |  | Fixed
2026-03-26 | Check generate questions with valid data | IT | Software Package | Question Generator | Đạt |  | Fixed
2026-03-26 | Check filter by status (Approved) | IT | Software Package | Question Submissions | Đạt |  | Fixed
2026-03-26 | Check view question detail | IT | Software Package | Question Review | Đạt |  | Fixed
2026-03-30 | Opening schedule does not display dates | Review | Software Package | Course/Class Schedule | Đức Anh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Opening schedule is fixed at 7-day intervals and only shows the nearest classes | Review | Software Package | Course/Class Schedule | Đức Anh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Registration page allows temporary emails (Mailtrap) | Review | Software Package | Authentication | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing permission field when Expert creates a course (user can edit the entire course) | Review | Software Package | Course Management | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Course avatar does not support file upload | Review | Software Package | Course Management | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Course description does not support HTML input | Review | Software Package | Course Management | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing Setting List page | Review | Software Package | System Management | Đức Anh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Role display on the introduction page is incorrect/missing | Review | Software Package | User Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Admin does not inherit permissions from Expert and Manager | Review | Software Package | User Management | Đức Anh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Registration approval page is missing the Category column | Review | Software Package | Admin Dashboard | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Registration approval page lacks filtering functionality | Review | Software Package | Admin Dashboard | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Manager page is missing columns: Course Name, Class Name, Teacher, Status | Review | Software Package | Manager Dashboard | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Manager page lacks filters by Course, Class, Teacher, Status | Review | Software Package | Manager Dashboard | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Class creation: status is not using radio buttons | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | End date is not auto-generated and cannot be edited | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Schedule does not support free input or checkbox selection | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing class description field (2–3 lines) | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Number of sessions is not displayed at the top | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing student management page for classes (Manager) | Review | Software Package | Class Management | Tứ |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | “My Teaching Schedule” shows redundant student lists | Review | Software Package | Teacher Dashboard | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | “My Teaching Schedule” lacks session, date, time, room, and limit information | Review | Software Package | Teacher Dashboard | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | “Students in My Class” page lacks filters by class/course/status | Review | Software Package | Teacher Dashboard | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | “Students in My Class” page lacks search functionality | Review | Software Package | Teacher Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Course content page: missing dropdown arrow icon next to title | Review | Software Package | Expert Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Course content page: still displays unnecessary header row | Review | Software Package | Expert Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Add/Edit/Delete lesson buttons are not positioned properly | Review | Software Package | Expert Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Newly created chapters do not auto-expand | Review | Software Package | Expert Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Adding a new lesson does not display upload/download form by type | Review | Software Package | Expert Dashboard | Đạt |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Quiz creation page does not support adding by chapter | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Quiz question selection lacks import / AI generation | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing quiz classification (listening, speaking, reading, writing) | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing question group combobox | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Does not support drag-and-drop question ordering | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Allows editing quiz after creation (should be disabled) | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Does not display fields per skill type | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | AI generation lacks level and topic inputs | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Speaking exercises do not support direct recording | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing question difficulty level input | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | No duplicate question detection (≥70%) | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing tab to display duplicate percentage | Review | Software Package | Quiz Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Save/Cancel buttons are incorrectly positioned | Review | Software Package | Global UI | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Popup is displayed in the wrong position (right side) | Review | Software Package | Global UI | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Teacher page has no permission restrictions (should only add lessons, not chapters) | Review | Software Package | Teacher Dashboard | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | List page missing tabs: learning info, schedule, class details, students, online content | Review | Software Package | Class Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Lessons are not displayed in dropdown format | Review | Software Package | Class Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Chapters are not mapped to sessions | Review | Software Package | Class Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Schedule does not allow editing | Review | Software Package | Class Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Class creation does not auto-create sections | Review | Software Package | Class Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing practice exercise functionality | Review | Software Package | Learning Module | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing grading functionality | Review | Software Package | Learning Module | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Evaluation page lacks filters by class and instructor | Review | Software Package | Learning Module | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Live class has not been removed | Review | Software Package | Learning Module | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Course types (content vs class-based) are not clearly separated | Review | Software Package | Course Management | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Missing gradebook | Review | Software Package | Learning Module | Thanh |  | Fixed |  | Linh update Report 3 (SRS)
2026-03-30 | Students cannot view grades within each course | Review | Software Package | Student Dashboard | Thanh |  | Fixed |  | Linh update Report 3 (SRS)